## Visit report
D-TI-GR-032 |  | Visit / Inspection report
Report no. |  | 25380-SEA-JNO-PR001-20260305 | [5 empty] | Report rev. |  | 0-0
Location / address |  | Frejasvej 4, 6950 Ringkøbing, Denmark + Mamrelund 9, 6960 Hvide Sande | [5 empty] | Visit date |  | 2026-03-05
Inspector |  | Jelle Nuyens
Project name |  |  | Baltyk II & III
Project ref. no. |  |  | 25380
Contract ref. |  |  | 25380
Smulders contact name |  |  | Ebo Lantiga / Maarten Vanstappen
Scope of supply |  | Follow up inspections Seasight davits - FAT + Visual assessment, hardness testing, coating inspection
Reference docs |  | 08.00.00.25 - NL1Q 25380 HKW VII ITP_Rev02 | [6 empty] | Rev. | 2
Rev.
Rev.
Rev.
Rev.
Rev.
Present |  |  |  |  | Representing
| Jelle Nuyens |  |  |  | Representing |  | Inspector - Smulders/Iemants
Representing
Representing
Representing
Representing
Representing
Agenda
[5 empty] | 1 | Health, Safety, Security & Environment
[5 empty] | 2 | Contractual
[5 empty] | 3 | Procurement
[5 empty] | 4 | Work preparation
[5 empty] | 5 | Planning / Progress
[5 empty] | 6 | Daily activity
[5 empty] | 7 | Issues / observations / NCR
[5 empty] | 8 | Risks
[5 empty] | 9 | Any other business
[5 empty] | 10 | Evidence documentation
Result | Accepted with comments
Date of next scheduled visit
Purpose of next scheduled visit
Prepared by |  | Jelle Nuyens |  |  |  | Signature
Visit / Inspection purpose
Follow up inspections Seasight davits - FAT + Visual assessment, hardness testing, coating inspection
1. Health, Safety, Security & Environment
HSSE conditions acc. to requirements
Observations
2. Contractual
Contract / Purchase Order signed by both parties
Advance Payment Bond valid
Performance Bond valid
Warranty Bond valid
Parent Company Guarantee valid
Other
3. Procurement
Materials ordered as required
Deliveries done / confirmed as required
Quality of delivered materials acc. to requirements
Observations
4. Work preparation
Workshop drawings ready / planned as required
Correct revisions available
Correct revisions of drawings used in workshop
Other
5. Planning / Progress
Correct planning available
Progress details |  |  | MACH |  | ASSY & WELD |  | SURF. TREATM |  | AS BUILT |  | TIMING
ITEM |  |  | % | Latest finish | % | Latest finish | % | Latest finish | % | Latest finish
|  |  | 0% |  | 0% |  | 0% |  | 0%
|  |  | 0% |  | 0% |  | 0% |  | 0%
|  |  | 0% |  | 0% |  | 0% |  | 0%
|  |  | 0% |  | 0% |  | 0% |  | 0%
|  |  | 0% |  | 0% |  | 0% |  | 0%
Other
6. Daily activity / Inspection visit
Date | 2026-03-04
Welding inspection: heat input verification, hardness testing on cutting surfaces, preheating checks per WPS. Reference observations on other customer flange seams.
Date | 2026-03-05
FAT tests witnessed (cranes 14, 16, 18, 19). Coating inspection on cranes 2, 4, 5, 6 — pinholes found, repair indicated. Holiday Detector planned.
Date
Date
Date
Date
Date
7. Issues /observations / NCR
Description |  |  |  | Improvement proposal |  |  |  |  | Owner | Due | Status
Hardness on cutting surface: 630HV avg — NOT according to procedure (3 measurements) |  |  |  | Grinding/re-machining required. Re-test after correction. |  |  |  |  | Seasight |  | Open
Pinholes in paint coating on cranes 2, 4, 5, 6 |  |  |  | Repair + Holiday Detector final inspection. |  |  |  |  | Seasight |  | Open
Round seam of flange — other customer piece always at least a4 |  |  |  | Review weld sizing against drawing requirements. |  |  |  |  | Smulders |  | Open
8. Risks
Description | [8 empty] | Owner |  | Status
9. Any other business
10. Evidence documentation
Heat input acceptable according to WPS | [5 empty] | Welding acceptable
[Picture] | [5 empty] | [Picture]
Welding acceptable | [5 empty] | Welding acceptable
[Picture] | [5 empty] | [Picture]
Welding good — preheated according to WPS | [5 empty] | Hardness 630HV — NOT according to procedure
[Picture] | [5 empty] | [Picture]
Hardness — NOT according to procedure | [5 empty] | Hardness — NOT according to procedure
[Picture] | [5 empty] | [Picture]
Other customer: flange round seam always at least a4 | [5 empty] | Reference observation flange seam
[Picture] | [5 empty] | [Picture]
FAT test crane 18 — witnessed and finished | [5 empty] | FAT test crane 16 — witnessed and finished
[Picture] | [5 empty] | [Picture]
FAT test crane 19 — witnessed and finished | [5 empty] | FAT test crane 14 — witnessed and ongoing
[Picture] | [5 empty] | [Picture]
Crane 5: pinholes — repair indicated + Holiday Detector | [5 empty] | Crane 5: pinholes
[Picture] | [5 empty] | [Picture]
Crane 5: pinholes | [5 empty] | Crane 5: pinholes
[Picture] | [5 empty] | [Picture]
Crane 5: pinholes | [5 empty] | Crane 4: same problem, indicated, ready to finish
[Picture] | [5 empty] | [Picture]
Crane 4: pinholes | [5 empty] | Crane 4: pinholes
[Picture] | [5 empty] | [Picture]
Crane 4: pinholes | [5 empty] | Crane 4: pinholes
[Picture] | [5 empty] | [Picture]
Crane 2: same pinhole problem | [5 empty] | Crane 2: pinholes
[Picture] | [5 empty] | [Picture]
Crane 2: pinholes | [5 empty] | Crane 2: pinholes
[Picture] | [5 empty] | [Picture]
Crane 2: pinholes | [5 empty] | Crane 2: pinholes
[Picture] | [5 empty] | [Picture]
Crane 6: back pinholes — same as other 3 | [5 empty] | Crane 6: pinholes
Crane 6: pinholes | [5 empty] | Crane 6: pinholes
Crane 6: pinholes | [5 empty] | Crane 6: pinholes
Crane 6: pinholes
Note on D5: Mick Thys: Naming convention: PPPPP-SSS-III-RPxxx-yyyymmdd 25150-MAR-SPI-RP001-20200625 PPPPP = Project number (e.g. 25150) SSS = Subcontractor initials, first 3 letters (e.g. MAR for Marketex) III = Inspector initials, first letter of name + 2 first letters of surname (e.g. SPI for Serge Pironet) RPxxx = Report number (e.g. RP001 for first report of this subcontractor) yyyymmdd = Inspection date (e.g. 20200625 for 25th of June 2020)
Note on E90: Mick Thys: Yellow marked columns to be adjusted to reflect the actual process steps of the applicable scope of works

## Lists
Result | YES/NO | YES/NO/NA | OK/NOK | Issue status | Risk status | Inspection type
Accepted | YES | YES | OK | Open | Open | Daily activity
Accepted with comments | NO | NO | NOK | Closed | Obsolete | Inspection visit
Rejected |  | N/A