## Visit report
D-TI-GR-032 | Visit / Inspection report
Report no. | [6 empty] | Report rev. |  | 0-0
Location / address | [6 empty] | 03/03/2026
Inspector
Project name |  | DAVIT CRANES 25380
Project ref. no. |  | DAVIT CRANES 25380
Contract ref. |  | 25390
Smulders contact name |  | Ebo Lantiga / Maarten Vanstappen
Scope of supply | all
Reference docs | [7 empty] | Rev.
Rev.
Rev.
Rev.
Rev.
Rev.
Present |  |  |  | Representing
Representing
Representing
Representing
Representing
Representing
Representing
Agenda
|  |  |  | 1 | Health, Safety, Security & Environment
|  |  |  | 2 | Contractual
|  |  |  | 3 | Procurement
|  |  |  | 4 | Work preparation
|  |  |  | 5 | Planning / Progress
|  |  |  | 6 | Daily activity
|  |  |  | 7 | Issues / observations / NCR
|  |  |  | 8 | Risks
|  |  |  | 9 | Any other business
|  |  |  | 10 | Evidence documentation
Result
Date of next scheduled visit
Purpose of next scheduled visit
Prepared by | QC Vault Bot (auto-generated) |  |  |  | Signature
Visit / Inspection purpose
all
1. Health, Safety, Security & Environment
HSSE conditions acc. to requirements
Observations
2. Contractual
Contract / Purchase Order signed by both parties
Advance Payment Bond valid
Performance Bond valid
Warranty Bond valid
Parent Company Guarantee valid
Other
3. Procurement
Materials ordered as required
Deliveries done / confirmed as required
Quality of delivered materials acc. to requirements
Observations
4. Work preparation
Workshop drawings ready / planned as required
Correct revisions available
Correct revisions of drawings used in workshop
Other
5. Planning / Progress
Correct planning available
Progress details |  | MACH |  | ASSY & WELD |  | SURF. TREATM |  | AS BUILT |  | TIMING
ITEM |  | % | Latest finish | % | Latest finish | % | Latest finish | % | Latest finish
|  | 0% |  | 0% |  | 0% |  | 0%
|  | 0% |  | 0% |  | 0% |  | 0%
|  | 0% |  | 0% |  | 0% |  | 0%
|  | 0% |  | 0% |  | 0% |  | 0%
|  | 0% |  | 0% |  | 0% |  | 0%
Other
6. Daily activity / Inspection visit
Date
Date
Date
Date
Date
Date
Date
7. Issues /observations / NCR
Description |  |  | Improvement proposal |  |  |  |  | Owner | Due | Status
Davit Crane 25380 Seasight Vt Rep Mt Mar: porosity,undercut |  |  | Visible NDT chalk markings "Mana VT-KMP / MT" are present on the main vertical p |  |  |  |  | Inspector | 03/03/2026 | Open
Davit Crane 25380 Fastener Hole Paint De: spatter |  |  | Minor coating defects, characterized by an uneven and textured paint finish, are |  |  |  |  | Inspector | 03/03/2026 | Open
25380 Davit Crane Paint Seam Ripples Por: porosity,pinhole,pinholes,runs,sags |  |  | Visual inspection (VT) of a coated weld seam on a davit crane component reveals |  |  |  |  | Inspector | 03/03/2026 | Open
Davit Crane Weld Undercut Marked: undercut |  |  | Undercut defect is visible and marked with green chalk on a weld seam of a struc |  |  |  |  | Inspector | 03/03/2026 | Open
Davit Crane 25380 Qc Pre Mt: undercut |  |  | Inspector's markings, including "RQ" and a green line along the upper horizontal |  |  |  |  | Inspector | 03/03/2026 | Open
Davit Cranes 25380 Weld Marker Line Pre |  |  | An unevenly textured green coating is visible adjacent to a vertical fillet weld |  |  |  |  | Inspector | 03/03/2026 | Open
Set 1 Eindkrater Corner Buildup: end crater |  |  | Visual inspection (VT) of Set 1 reveals a prominent weld end crater, visible as |  |  |  |  | Inspector | 03/03/2026 | Open
8. Risks
Description | [7 empty] | Owner |  | Status
9. Any other business
10. Evidence documentation
Davit Crane 25380 Seasight Vt Rep Mt Markings — porosity,undercut () |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | Davit Crane 25380 Fastener Hole Paint Defect — spatter ()
[Picture] |  |  |  |  | [Picture]
25380 Davit Crane Paint Seam Ripples Pores — porosity,pinhole,pinholes,runs,sags () |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | Davit Crane Weld Undercut Marked — undercut ()
[Picture] |  |  |  |  | [Picture]
Davit Crane 25380 Qc Pre Mt — undercut () |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | Davit Cranes 25380 Weld Marker Line Pre Ndt — ()
[Picture] |  |  |  |  | [Picture]
Set 1 Eindkrater Corner Buildup — end crater () |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | Crane30 Weld Textured Coating — ()
[Picture] |  |  |  |  | [Picture]
Davit Crane Components Pending Vt Mt — () |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
[Description] |  |  |  |  | [Description]
[Picture] |  |  |  |  | [Picture]
Note on D5: Mick Thys: Naming convention: PPPPP-SSS-III-RPxxx-yyyymmdd 25150-MAR-SPI-RP001-20200625 PPPPP = Project number (e.g. 25150) SSS = Subcontractor initials, first 3 letters (e.g. MAR for Marketex) III = Inspector initials, first letter of name + 2 first letters of surname (e.g. SPI for Serge Pironet) RPxxx = Report number (e.g. RP001 for first report of this subcontractor) yyyymmdd = Inspection date (e.g. 20200625 for 25th of June 2020)
Note on E90: Mick Thys: Yellow marked columns to be adjusted to reflect the actual process steps of the applicable scope of works

## Lists
Result | YES/NO | YES/NO/NA | OK/NOK | Issue status | Risk status | Inspection type
Accepted | YES | YES | OK | Open | Open | Daily activity
Accepted with comments | NO | NO | NOK | Closed | Obsolete | Inspection visit
Rejected |  | N/A